## Framework
TIMELINE | [5 empty] | CONTRIBUTIONS |  |  | TASK TABLE
Milestone | Timeline | Task | Deliverable | Team Member | Deadline | Item | Team Member | Contributions | ID | Task | Team Member | File/Function | Deliverable | Status
Understand concepts of quantum searching | October | Research Grover's algorithm and basics of quantum computing | Planning doc of prospective design ideas | Amanda and Savannah | 2026-10-31 | Iteration #1 | Amanda | created timeline, contributed to objectives, scope, and technologies and tools | 0 | Create menu and stubs | Amanda | main.cpp: main(), tasks.h/.cpp: printMenu(), runMenu() | program compiles and menu options print "not yet implemented" | In Progress
Agree on program design | November W1 | Set up GitHub Repo | GitHub repo with README, folders, .gitignore | Savannah | 2026-11-06 |  | Savannah | Helped form document with objectives, plan, tools, and communication details | 1 | Dataset generation | Savannah | data_generator.h/.cpp, tasks.cpp: generateDataset() | User picks N and gets a random unsorted list and target | Stub
|  | Create program class design | Diagram of program design with classes | Amanda | 2026-11-06 | Iteration #2 | Amanda |  | 2 | Impl. Linear serach | Savannah | linear_search.h/.cpp, linearSearch() | Returns correct index and query count | Stub
Classical search implemented | November W2 | Implement linear and binary search algorithms | Search classes pass tests | Savannah | 2026-11-12 |  | Savannah |  | 3 | Impl. Binary search | Savannah | binary_search.h/.cpp, binarySearch() | Returns correct index and query count | Stub
|  | Implement breadth-first and depth-first search algorithms | Search classes pass tests | Amanda | 2026-11-12 | Iteration #3 | Amanda |  | 4 | Impl. Breadth-first search | Amanda | breadthfirst_search.h/.cpp, breadthFirstSearch() | Returns correct index and nodes visited | Stub
|  | Write test classes | Test class for each algorithm using dataset of integers | Amanda and Savannah | 2026-11-16 |  | Savannah |  | 5 | Impl. Depth-first search | Amanda | depthfirst_search.h/.cpp, depthFirstSearch() | Returns correct index and nodes visited | Stub
Quantum search implemented | November W3-4 | Implement grover's algorithm | Search class passes tests | Savannah and Amanda | 2026-11-20 | Iteration #4 | Amanda |  | 6 | Impl. Quantum state simulator | Amanda | quantum_state.h/.cpp | returns oracle and diffusion verified on small N | Stub
|  | Write test class | Test class algorithm using dataset of integers | Amanda | 2026-11-24 |  | Savannah |  | 7 | Impl. Grover's search | Amanda and Savannah | grover_search.h/.cpp, groverSearch() | Measured index, oracle queries, iterations, and success probability | Stub
Working demonstration of search comparisons | December W1 | Implement query and time counting for all algorithms | Program returns query, iteration, and time data for searches | Savannah | 2026-12-04 | Iteration #5 | Amanda |  | 8 | Impl. classical search tests | Savannah | tests.h/.cpp: testLinear(), testBinary(), testBreadthFirst(), testDepthFirst(), classicalTests() | returns pass/fail output for edge cases: target first, last, absent, N=1 | Stub
[9 empty] | 9 | Impl. Grover search tests | Amanda | tests.cpp: testGrover(), groveryTests() | success rate over many trials > expected probability
|  | Implement comparison driver | Program returns table of data comparing algorithm queries and success | Amanda | 2026-12-04 |  | Savannah |  | 10 | Impl. Query and time counting | Amanda | timer.h/.cpp, search(), performanceReport() | one-run table of queries and time for all algorithms | Stub
Final report and presentation completed | December W2 | Create presentation slides | Complete slide deck | Amanda and Savannah | 2026-12-11 | Iteration #6 | Amanda |  | 11 | Impl. Comparison driver | Savannah | comparison_driver.h/.cpp, comparisonTable() | table across various N showing average queries, time, and success rate | Stub
|  | Write Final Report | Complete report | Amanda and Savannah | 2026-12-11 |  | Savannah |  | 12 | README and build instructions | Amanda | README.md | Build/run steps verified on a clone | Stub
[9 empty] | 13 | Write report | Amanda and Savannah | docs/ | updated task table, timeline, contributions, and report | Stub

## status_chip
In Progress
Stub
Complete